## Ark1
| PLANNING |  |  |  |  | DESIGN |  |  |  |  | DEVELOPMENT |  |  |  |  | LAUNCH
| DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14 | DAY 15 | DAY 16 | DAY 17 | DAY 18 | DAY 19 | DAY 20
Project Manager | • Management • Customer contact • Initial meeting • Goals • Planning | • Management • Customer contact • Assessment • Goals • Planning | • Management • Customer contact |  | • Meeting with client | • Management • Customer contact |  |  |  | • Final meeting (before developing) | • Management • Customer contact |  |  |  | • Meeting with customer before launching | • Management • Customer contact |  |  |  | • Processing • Launch
Usability Lead | • Planning • Research • Scheduling • Budgeting
Content Developer | • Initial meeting • Goals • Assessment • Planning | • Goals • Assessment • Planning • Research | • Research | • Content Planning • Outline |  | • Structure Planning | • Text development • Content development • Meeting with copywriter |  |  | • Final meeting (before developing) |  | • UX/UI planning |  |  | • UX/UI testing |  |  |  | • Processing • Refinement | • Processing • Launch
Graphic Designer | • Goals • Assessment • Planning |  |  | • Content Planning • Outline |  | • Structure Planning | • Moodboard • Styletile • Color palette |  |  | • Final meeting (before developing) | • Create wireframe |  | • UX/UI planning |  | • UX/UI testing |  |  |  | • Processing • Refinement | • Processing • Launch
Photographer | • Initial meeting • Goals | [5 empty] | • Photoshoot |  | • Photo editing | • Final meeting (before developing)
HTML Developer | • Initial meeting • Goals |  |  | • Content Planning • Outline | [6 empty] | • Coding • Integration • HTML |  |  |  |  | • Cross platform • Browser | • Cross platform • Browser • Validating |  | • Processing • Refinement | • Processing • Launch
CSS Developer | • Initial meeting • Goals |  |  | • Content Planning • Outline |  | • Structure Planning |  |  |  | • Final meeting (before developing) |  |  | • Coding • Styling • CSS |  |  | • Cross platform • Browser | • Cross platform • Browser • Validating |  | • Processing • Refinement | • Processing • Launch
Copywriter | • Initial meeting • Goals |  |  |  |  | • Structure Planning | • Text development • Content development • Meeting with content developer |  |  | • Final meeting (before developing) | [9 empty] | • Processing • Launch